## Sheet1
Group 1 - Revision Table
Sprint 1
Date | Description | Discussion | Personnel
2014-11-23 | Create Initial Data File | Created Data File and added URL and Description for each Lift/WOD | Stephen
2014-11-24 | Created Initial PR2 Main | Created Initial PR2 Main to read Data File | Luis
2014-11-24 | Created Initial GUIs | Developed Initial Draft GUIs to display data passed from Main | Tracy
2014-11-25 | Created Lift and WOD Objects | Developed Lift and WOD objects to better handle data elements | Luis
2014-11-25 | Modified Initial Data File | Modified Initial Data File to match Luis' code and remove hidden formatting | Stephen
2014-11-25 | Modified GUIs | Modified GUIs and successfully linked data. Made graphical enhancements. | Tracy
2014-11-26 | To and From Data File | Completed the To and From Data file Methods | Luis
2014-11-26 | Completed GUI Modifications | Standardized the GUIs to give them a uniform and more professional look. Also, changed the buttons | Tracy
2014-11-26 | Completed the Backup Data File | Completed the Backup Data File to ensure that if the primary data file is corrupted it can be read from the last known-good backup | Stephen
2014-11-27 | Thanksgiving | Sent group a tutorial on using GitHub with NetBeans | Stephen
2014-11-28 | Backup Error Handling | Added method to update Backup Data File upon successful read from primary data file | Luis
2014-11-28 | Combined Code | Combined and posted the most recent code from each member to GitHub. | All
2014-11-29 | Error Handling | Complete the user-input validations for 1RM, Notes, and Time | Stephen
2014-11-29 | URL Activation | Modified URLs to allow user to open them. | Tracy